## Orders
Order ref | Part # | Revision | Description | Qty | Priority | Required at CAMCO | Customer due date | SO required? | Subcontracting required? | Decision note | Team member | Responsible person | Communication ref | SO # | PO # | BPO # | Batch | Part sent to team | China quotation received | Quote submitted to Rich | Review status | Quote approved | SO requested | SO request to costing manager | SO number received | PO prep started | PO completed | PO sent for verification | PO verified | PO sent to vendor | Vendor acknowledged | Production started | Production completed | Vendor shipped | Arrived at CAMCO | Expected production completion | Expected shipment | Expected arrival at CAMCO | Next follow-up date | Next action | Outstanding issue | Last update | Escalated? | Note | Down payment made | Forwarder pickup | Departed origin port | Arrived at destination port | Moved to inspection | Moved to stock | Qty shipped | Qty received | Qty on hold | Qty rejected | Qty moved to stock
Note on A1: Unique reference of this order. Leave blank for a new order: the app assigns SUB-0001, SUB-0002 ... and the export shows it. Use it to update the order later.
Note on B1: CAMCO part number. Required.
Note on E1: Required quantity (pcs). Leave blank while it is not known: the order is flagged until you enter it.
Note on F1: NORMAL (default), HIGH or LINE DOWN. HIGH and LINE DOWN are followed up daily.
Note on G1: Date the parts are needed at CAMCO.
Note on I1: Is a Shop Order needed? YES, NO or PENDING.
Note on J1: Can the part be made by the subcontractor (China)? YES, NO or PENDING. NO closes the order as not required.
Note on K1: The reason, especially when the answer is NO.
Note on L1: Responsible subcontractor team member.
Note on M1: Who must act next.
Note on N1: Email subject or link.
Note on O1: Subcontractor SO number from the costing manager.
Note on P1: PO number for the vendor. Must be unique.
Note on S1: Date the part number was sent to the subcontractor team. Starts the quotation clock.
Note on V1: Review status with Rich. Suggested: SUBMITTED, IN REVIEW, CHANGES REQUESTED, APPROVED. Other wording is kept as written.
Note on W1: Date the team confirmed the approval.
Note on AJ1: Confirmed arrival. Completes the order.
Note on AK1: Promised dates. If one changes, the app keeps the original and logs the change.
Note on AQ1: Date of the last update from the team or vendor.
Note on AR1: YES or NO.

## How to use
Subcontractor orders: Excel template
1. Fill in the Orders sheet: one row per order (one part sent to the subcontractor team).
2. Save the file, then in the app open Subcontractor and click Import Excel. You get a preview (new, updated, problems) before anything is saved.
3. To update orders later: click Export Excel in the app. It gives you this same sheet with your current data and each order's Order ref. Change cells, add dates, upload again.
Rules
Only filled cells are imported. A blank cell never erases what is already in the app.
An order is matched by its Order ref (or by its PO # if there is no ref). A row without a ref or a known PO # is a new order and gets the next SUB-0001 style ref.
Required for a new order: Part # and Qty. Everything else can be added later as the order moves.
Dates: use yyyy-mm-dd (for example 2026-11-30) or normal Excel dates. Calendar days are used for all elapsed-time figures.
When a date that is already in the app changes, the app keeps the original date and records the change in the order's log.
The stage of each order (quotation, approval, SO, PO, production, shipment, arrived) is worked out from the dates you enter. Nothing is assumed done without a date.
Column | Group | What to enter
Order ref | Order | Unique reference of this order. Leave blank for a new order: the app assigns SUB-0001, SUB-0002 ... and the export shows it. Use it to update the order later.
Part # * | Order | CAMCO part number. Required.
Revision | Order | Free text.
Description | Order | Free text.
Qty | Order | Required quantity (pcs). Leave blank while it is not known: the order is flagged until you enter it.
Priority | Order | NORMAL (default), HIGH or LINE DOWN. HIGH and LINE DOWN are followed up daily. Allowed: NORMAL, HIGH, LINE DOWN.
Required at CAMCO | Order | Date the parts are needed at CAMCO.
Customer due date | Order | A date.
SO required? | Decision | Is a Shop Order needed? YES, NO or PENDING. Allowed: YES, NO, PENDING.
Subcontracting required? | Decision | Can the part be made by the subcontractor (China)? YES, NO or PENDING. NO closes the order as not required. Allowed: YES, NO, PENDING.
Decision note | Decision | The reason, especially when the answer is NO.
Team member | People | Responsible subcontractor team member.
Responsible person | People | Who must act next.
Communication ref | People | Email subject or link.
SO # | Numbers | Subcontractor SO number from the costing manager.
PO # | Numbers | PO number for the vendor. Must be unique.
BPO # | Order | Free text.
Batch | Order | Free text.
Part sent to team | Quotation | Date the part number was sent to the subcontractor team. Starts the quotation clock.
China quotation received | Quotation | A date.
Quote submitted to Rich | Quotation | A date.
Review status | Quotation | Review status with Rich. Suggested: SUBMITTED, IN REVIEW, CHANGES REQUESTED, APPROVED. Other wording is kept as written.
Quote approved | Quotation | Date the team confirmed the approval.
SO requested | Subcontractor SO | A date.
SO request to costing manager | Subcontractor SO | A date.
SO number received | Subcontractor SO | A date.
PO prep started | Purchase order | A date.
PO completed | Purchase order | A date.
PO sent for verification | Purchase order | A date.
PO verified | Purchase order | A date.
PO sent to vendor | Purchase order | A date.
Vendor acknowledged | Vendor & production | A date.
Production started | Vendor & production | A date.
Production completed | Vendor & production | A date.
Vendor shipped | Shipment & arrival | A date.
Arrived at CAMCO | Shipment & arrival | Confirmed arrival. Completes the order.
Expected production completion | Expected dates | Promised dates. If one changes, the app keeps the original and logs the change.
Expected shipment | Expected dates | A date.
Expected arrival at CAMCO | Expected dates | A date.
Next follow-up date | Follow-up | A date.
Next action | Follow-up | Free text.
Outstanding issue | Follow-up | Free text.
Last update | Follow-up | Date of the last update from the team or vendor.
Escalated? | Follow-up | YES or NO.
Note | Follow-up | Free text.
Down payment made | Optional logistics | A date.
Forwarder pickup | Optional logistics | A date.
Departed origin port | Optional logistics | A date.
Arrived at destination port | Optional logistics | A date.
Moved to inspection | Optional logistics | A date.
Moved to stock | Optional logistics | A date.
Qty shipped | Optional | A number.
Qty received | Optional | A number.
Qty on hold | Optional | A number.
Qty rejected | Optional | A number.
Qty moved to stock | Optional | A number.

## Example
Order ref | Part # | Revision | Description | Qty | Priority | Required at CAMCO | Customer due date | SO required? | Subcontracting required? | Decision note | Team member | Responsible person | Communication ref | SO # | PO # | BPO # | Batch | Part sent to team | China quotation received | Quote submitted to Rich | Review status | Quote approved | SO requested | SO request to costing manager | SO number received | PO prep started | PO completed | PO sent for verification | PO verified | PO sent to vendor | Vendor acknowledged | Production started | Production completed | Vendor shipped | Arrived at CAMCO | Expected production completion | Expected shipment | Expected arrival at CAMCO | Next follow-up date | Next action | Outstanding issue | Last update | Escalated? | Note | Down payment made | Forwarder pickup | Departed origin port | Arrived at destination port | Moved to inspection | Moved to stock | Qty shipped | Qty received | Qty on hold | Qty rejected | Qty moved to stock
| CHN-1001 | B | Bracket, machined | 200 | NORMAL | 2027-02-15 |  | YES | YES |  | Li Wei | [6 empty] | 2026-10-28
SUB-0002 | CHN-2040 |  |  | 500 | HIGH | 2027-01-20 |  | YES | YES |  | Li Wei | [6 empty] | 2026-10-01 | 2026-10-09 | 2026-10-10 | IN REVIEW | [17 empty] | 2026-11-03
SUB-0003 | CHN-3300 |  |  | 120 | NORMAL | 2026-12-30 | [7 empty] | S5002 | PO-78 |  |  | 2026-08-01 | 2026-08-10 |  |  | 2026-08-15 | 2026-08-16 |  | 2026-08-20 |  | 2026-08-26 |  | 2026-08-28 | 2026-08-29 | 2026-09-01 | 2026-09-05 |  |  |  | 2026-10-30 |  | 2026-12-10
These rows only show how a sheet looks. Copy what you need into the Orders sheet; this sheet is never imported.